Aegis-40 FER — Status Summary: Done vs. Remaining

Owner key

| Code | Role | Person |
| --- | --- | --- |
| LEAD | Team lead / front matter / assembly | (lead) |
| NEU | Neutronics & core | Samira, Laziz |
| TH | Thermal-hydraulics & cycle | Adilbek, Samira |
| 3S | Safety, safeguards, I&C | Azamkhon, Shakhzod |
| LAY | Layout, auxiliary, economics | S. Alisher , Azamkhon, Shakhzod |

1. Big picture

The Section 8 technical body is complete in draft — a single consolidated master (Aegis40-FER-master.md, approx. 961 paragraphs / 47 tables), with every heading filled and none left blank (the pass/fail rule from last year's lead). The two largest items not yet in the document are the front matter (§1–§7) and the template / submission packaging. The single technical gate that still blocks final numbers is the STAT_FINAL OpenMC neutronics run.

2. Done — drafted and internally consistent

| § | Section | Owner | What is done |
| --- | --- | --- | --- |
| 8.1 | General description | LEAD/NEU | All parameter tables, codes & standards, regulatory list, prep-phase docs |
| 8.2 | Core design | NEU | Materials, geometry, layout figures; neutronics V&V + NuScale anchor (Tables 8.2-6/8.2-7). Numeric neutronics values pending STAT_FINAL |
| 8.3 | Fuel & material | NEU | Linear heat rate, centerline-temperature stack-up (CFD-based, 734 °C), fission-gas release, clad integrity |
| 8.4 | Cooling circuit | TH | Natural-circulation loop re-derived (H_tc 4.0 m, flow 467 kg/s, driving head 3.67 kPa, ~10 m vessel); heat removal closed by conjugate CFD (MDNBR 1.56, PCT 349 °C); ASME V&V-20 verified; validated vs NuScale NPM-160 |
| 8.5 | Safety criteria | 3S/TH | Criteria framework, demonstrated-margins table, defence-in-depth, dual heat sinks |
| 8.6 | Safety systems | 3S/TH | Passive ESF, two diverse shutdown means (EBIS), event-tree results for LOHS and SBO |
| 8.7 | I&C | 3S | Architecture, RPS/ESFAS/DAS, control room & human factors, digital twin |
| 8.8 | Auxiliary systems | LAY | System table, cogeneration isolation, electrical summary |
| 8.9 | Energy conversion | TH/LAY | Rankine cycle, state points, OTSG feasibility, TCES district heat + charging-duty justification, hydrogen |
| 8.10 | Layout | LAY | Three-island scheme, building inventory, critical piping |
| 8.11 | Waste management | LAY/NEU | Back-end plan, source term, decay heat, storage criticality (15/15 unit tests) |
| 8.12 | Economics | LAY | LCOE methodology, result, reference-reactor comparison (literature CAPEX) |
| 8.13 | Digital Appendix (V&V index) | ALL | Structure complete; some confirmatory runs pending |
| — | Provenance table | ALL | Every headline number traced to a basis class |
| — | Requirements-coverage matrix | ALL | Every §8 requirement mapped, with an honest could-not-close list |

3. Remaining — what is left to do

3.1 The one true gate — neutronics STAT_FINAL

| Item | Owner | Note |
| --- | --- | --- |
| Run STAT_FINAL OpenMC depletion; swap all [37FA-PENDING] markers (k_eff, burnup, cycle length, peaking, coefficients, rod worth, SDM, inventory) | Laziz | Also triggers the MDNBR |

3.2 Open analysis items (from the could-not-close list)

| Item | Owner |
| --- | --- |
| DBA spectrum depth — MSLB/SBLOCA event trees + quantitative CDF/LRF (2 initiators analysed today; rest screened; class-target CDF/LRF stated, not computed) | Adilbek or Azamkhon |
| Containment design pressure / P-T response — open dry-vs-pool concept decision | Azamkhon, Shakhzod |
| LOCA-transient PCT / clad-oxidation / ECR envelope (accident side, gated by DBA work) | Adilbek, Azamkhon, Shakhzod |
| Bottom-up CAPEX + cogeneration revenue credit (§8.12) — needs frozen equipment list |  |
| Site/interface studies — tritium permeation, Sinop coastal hazard, SKKY thermal discharge, EPZ dose |  |

3.3 Manual fixes (tool-specific, not code-fixable from the report)

| Item | Owner |
| --- | --- |
| CAD/Creo: vessel height to ~10 m / H_tc 4.0 m + STEP + general-arrangement drawing | Samira |
| DWSIM: secondary flowsheet primary flow 483→467 + cogeneration extraction tap | Samira |
| NuScale [verify] cells in Table 8.2-7 — pin 5 figures against the FSAR (HM loading, specific power, rod count, cycle length, discharge burnup) | Samira |
| §8.10: reactor-building height vs ~10 m vessel | Shakhzod |

3.4 Figures / "shine" pass (the single biggest scoring lever)

| Item | Owner |
| --- | --- |
| Per-system P&IDs for §8.8; single-line electrical diagram for §8.8.10 | Shakhzod |
| 2D/3D layout plans + structural/weight data for §8.10.5 (CAD held locally) |  |
| Neutronics figures (k_eff-vs-burnup, radial/axial power maps) once STAT_FINAL lands |  |

3.5 Front matter §1–§7 — NOT STARTED (largest gap outside §8)

The master is §8-only. The template also requires the following. Source material exists (CAREM / Santinello / NuScale PDFs, safeguards and domesticity notes) but none of it is drafted into the document yet.

| § | Section | Owner |
| --- | --- | --- |
| 1 | Abstract / scope | LEAD |
| 2 | Team (schematic) | LEAD |
| 3 | Literature review | LEAD |
| 4 | Methodology / feasibility | LEAD |
| 5 | Originality / domesticity | 3S/LEAD |
| 6 | Work plan | LEAD |
| 7 | Broader impacts | LEAD |

3.6 Digital Appendix packaging

| Item | Owner |
| --- | --- |
| Run the cheap confirmatory benchmarks in WSL (BEAVRS pincell depletion, ICSBEP) — scripted, not yet executed | NEU |
| Assemble the ZIP: one sample input per code + explanations (T-H th_cfd/ case ready; OpenMC decks + economics deck need bundling) | ALL |

3.7 Template compliance + submission (pass/fail logistics)

| Item | Owner |
| --- | --- |
| Official template .docx styling (Arial 12 / Arial Black 14, margins, TOC, ≤120 pp); merge citations into one list; remove personal info; delete notes page | LEAD |
| Cross-review (each section read by a non-author); lock numbers across sections | ALL |
| Early-submission insurance upload before the deadline hour | LEAD |